# Consciousness Science 2026 — Project Milestones

| # | MILESTONES | Action Step | Deliverable | Who | Start | Due | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Website launch | Build single-page conference site with speakers, themes, venue, organizers | index.html — responsive site with speaker cards, theme cards, organizer grid | AD | Feb 2026 | Feb 2026 | Complete |
| 2 | Code of Conduct | Draft and publish attendance & conduct policy | conduct.html — anti-harassment policy, reporting procedures, enforcement | AD | Feb 2026 | Feb 2026 | Complete |
| 3 | Program timetable | Create password-protected schedule (Sun–Fri) with all session types | program.html — login-gated timetable with color-coded blocks | AD, AJ | Feb 2026 | Mar 2026 | Complete |
| 4 | Session detail pages | Break out concurrent sessions and workshops into dedicated sub-pages | concurrent1-4.html, workshops.html — per-day detail pages with session menus | AD | Mar 2026 | Mar 2026 | Complete |
| 5 | Speaker confirmation tracking | Cross-reference speakers between program and site; color-code by status | Updated program.html and index.html; automated sync via update_speakers.py | AD, AJ | Mar 2026 | Mar 2026 | Complete |
| 6 | Epstein disclosure & vetting protocol | Publish transparency statement and 7-step donor/speaker screening protocol | vetting.html — Epstein acknowledgment, protocol steps, escalation policy | AD, SS, TB | Mar 2026 | Mar 2026 | Complete |
| 7 | Sponsorship page | Create sponsor tiers (Gold/Silver/Bronze) with pledge form | pledges.html — tier cards, IONS 501(c)(3) disclosure, Google Form link | AD, TB | Mar 2026 | Mar 2026 | Complete |
| 8 | Donor vetting — Cyan Banister | Run full 7-step screening on prospective donor | Vetting_Cyan_Banister.docx — risk score 0, clear for acceptance | AD | Mar 2026 | Mar 2026 | Complete |
| 9 | Speaker reconfirmation campaign | Contact all pending/unconfirmed speakers to reconfirm for San Diego | Confirmation status updated in spreadsheet and program; remove or replace non-respondents | AJ, AD | Mar 2026 | May 2026 | In progress |
| 10 | Registration & abstract submission | Set up registration system and call for abstracts for concurrent/poster sessions | Registration portal live; abstract submission form; reviewer assignment | AD, SS, TB | Apr 2026 | Jun 2026 | Not started |

Key: AD = Arnaud Delorme, AJ = Abi James, SS = Susan Schneider, TB = Thomas Brophy